## Executive Summary
Enterprise Cybersecurity Risk Register
IslandLink Business Services Ltd. (Fictional) ¦ Jamaica ¦ Project 2 — Phase 3
Enterprise Risks |  | Critical Inherent |  | High/Critical Residual |  | Treatments In Progress
22 |  | 19 |  | 6 |  | 5
Executive Risk Summary
The enterprise risk register consolidates 36 threat/vulnerability scenarios into business-level cybersecurity risks with accountable owners and treatment decisions. The most significant exposures are identity compromise, privileged-access takeover, ransomware, backup/recovery failure, legacy infrastructure, perimeter/VPN compromise, financial fraud and third-party remote-management risk. Residual risk improves materially after proposed controls, but several crown-jewel risks remain High because their business impact would still be severe if an event occurred.
Inherent Rating | Count | Share |  | Residual Rating | Count | Share
Low | 0 | 0% |  | Low | 0 | 0%
Moderate | 0 | 0% |  | Moderate | 16 | 72.73%
High | 3 | 13.64% |  | High | 6 | 27.27%
Critical | 19 | 86.36% |  | Critical | 0 | 0%
Immediate Management Priorities
Order | Risk / Action | Owner | Due | Why
1 | Universal MFA / remove VPN and cloud exemptions | IT Manager | 2026-09-15 | Closes a direct initial-access path affecting multiple crown jewels
2 | Payment-change verification + anti-impersonation controls | Finance Manager | 2026-09-30 | Reduces BEC and direct financial-fraud exposure
3 | Firewall/VPN firmware, MFA and rule review | IT Manager | 2026-10-15 | Protects primary internet/remote-access boundary
4 | Immutable backups + documented restore tests | IT Manager | 2026-10-31 | Preserves recovery from ransomware/destructive incidents
5 | Privileged-access governance + hardened admin access | IT Manager | 2026-10-31 | Reduces enterprise-wide administrator takeover risk

## Risk Register
Risk ID | Risk Title | Risk Statement | Source Scenario IDs | Affected Asset IDs | Business Service / Area | Risk Owner | Threat / Cause | Vulnerability / Condition | Existing Controls | Control Effectiveness | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Treatment | Treatment Rationale | Recommended Controls / Actions | Action Owner | Target Date | Status | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Risk Appetite Position | NIST CSF 2.0 Mapping | ISO/IEC 27001:2022 Mapping | Evidence / Traceability
R-01 | Business Email Compromise / Payment Fraud | A finance mailbox or related account could be compromised or impersonated, allowing fraudulent payment instructions or vendor banking changes to be processed. | TV-01; TV-16 | AST-004; AST-005; AST-011; AST-030 | Financial Operations | Finance Manager | Phishing, account takeover, impersonation, unauthorized banking/vendor-detail change | Payment-change verification is informal; finance impersonation protections and segregation-of-duties assurance are incomplete. | MFA on finance accounts; email filtering; accounting audit trail; finance approval process | Moderate | 5 | 5 | 25 | Critical | Mitigate | Financial fraud could cause direct material loss and reputational harm; risk exceeds appetite. | Implement dual verification for banking/vendor changes; enable advanced anti-impersonation controls; strengthen conditional access; configure anomalous-payment/change alerts; review accounting role separation. | Finance Manager / IT Security | 2026-09-30 | In Progress | 2 | 5 | 10 | High | Above Appetite | GV.RM; PR.AA; PR.AT; DE.CM; RS.AN | A.5.15; A.5.18; A.6.3; A.8.5; A.8.15 | Asset Inventory AST-004/005/011/030; Threat Matrix TV-01/16
R-02 | Executive Account Compromise | An executive cloud account could be compromised through targeted phishing or token theft, enabling impersonation, sensitive-data access, fraudulent approvals or follow-on attacks. | TV-02; TV-04 | AST-003; AST-010; AST-001; AST-002; AST-008 | Executive Operations / Corporate Email | CEO / IT Manager | Spearphishing, credential theft, session-token theft, malicious OAuth consent | Executives are high-value targets; cloud identity monitoring, app-consent governance and advanced impersonation protection are incomplete. | MFA; email filtering; endpoint protection; M365 audit/sign-in logs | Moderate | 4 | 5 | 20 | Critical | Mitigate | Executive identity compromise has enterprise-wide fraud and information-security consequences. | Enforce phishing-resistant MFA for executives; restrict OAuth consent; deploy high-risk sign-in policies; strengthen anti-impersonation; establish rapid token/session revocation procedure. | IT Security Analyst | 2026-10-15 | Not Started | 2 | 4 | 8 | Moderate | Above Appetite | PR.AA; PR.AT; DE.CM; RS.AN | A.5.16; A.5.17; A.6.3; A.8.5; A.8.16 | AST-003/010/001/002/008; TV-02/04
R-03 | Cloud Account Compromise from Incomplete MFA | User or remote-access accounts without strong MFA could be compromised through password spraying, credential stuffing or reused credentials, providing unauthorized access to cloud services or the corporate network. | TV-03; TV-20 | AST-001; AST-002; AST-006; AST-017 | Identity / Remote Access | IT Manager | Password spraying, stolen passwords, credential stuffing | MFA coverage is incomplete; some VPN/cloud accounts remain exempt and inactive-account review is inconsistent. | Admin MFA; partial user MFA; sign-in/VPN logs | Limited | 5 | 5 | 25 | Critical | Mitigate | Credential-based entry is highly likely and can lead to broad compromise. | Enforce MFA for all users and VPN accounts; disable legacy authentication; review dormant accounts monthly; implement risk-based conditional access and impossible-travel/anomalous-login alerts. | Systems Administrator | 2026-09-15 | In Progress | 2 | 4 | 8 | Moderate | Above Appetite | PR.AA; DE.CM; ID.RA | A.5.16; A.5.17; A.5.18; A.8.5; A.8.16 | AST-001/002/006/017; TV-03/20
R-04 | Privileged Identity / Administrator Takeover | Stale privileged roles, unmanaged legacy credentials or compromised administrator sessions could allow an attacker or insider to obtain broad control of cloud, network or endpoint systems. | TV-05; TV-06; TV-32; TV-36 | AST-002; AST-012; AST-031; AST-013 | Privileged Access / IT Administration | IT Manager | Privileged credential theft, valid-account abuse, credential dumping, secret leakage | Privileged assignments are not regularly recertified; admin work occurs from general-purpose workstations; some secrets remain outside the central vault. | MFA; password manager; EDR; audit logs | Limited | 5 | 5 | 25 | Critical | Mitigate | Privileged compromise could produce enterprise-wide control loss and destructive access. | Implement quarterly privileged-role review; deploy privileged access workstations or hardened admin profiles; centralize all admin secrets in vault; rotate legacy secrets; use separate admin accounts; enable privileged activity alerts. | IT Manager | 2026-10-31 | Not Started | 2 | 5 | 10 | High | Above Appetite | GV.RR; PR.AA; PR.PS; DE.CM | A.5.15; A.5.16; A.5.18; A.8.2; A.8.18 | AST-002/012/031/013; TV-05/06/32/36
R-05 | Ransomware / Enterprise File Encryption | A ransomware infection could spread from an endpoint or remote-access foothold into shared files and legacy infrastructure, encrypting data and disrupting business operations. | TV-07; TV-09; TV-31; TV-32 | AST-009; AST-018; AST-019; AST-020; AST-008 | Endpoint Workforce / Legacy File Services | IT Manager | Phishing, malware execution, credential theft, legacy exploitation, lateral movement | Mixed endpoint patch cadence, local-admin exceptions, legacy technical debt, inherited file permissions and limited monitoring increase lateral-movement potential. | EDR/AV; backups; M365 versioning; endpoint security controls | Limited | 5 | 5 | 25 | Critical | Mitigate | Ransomware could stop operations, cause data loss and trigger extended recovery. | Standardize patch SLA; remove unnecessary local admin; segment legacy servers; tighten file permissions; expand EDR coverage/tuning; block common ransomware execution paths; test ransomware containment playbook. | IT Security Analyst / Systems Administrator | 2026-11-15 | Not Started | 3 | 5 | 15 | High | Above Appetite | PR.PS; PR.AA; DE.CM; RS.MI; RC.RP | A.8.7; A.8.8; A.8.9; A.8.20; A.8.22 | AST-009/018/019/020/008; TV-07/09/31/32
R-06 | Backup Compromise / Recovery Failure | Attackers or technical failures could make backups unavailable, encrypted, deleted or unreliable, preventing timely recovery from ransomware or infrastructure failure. | TV-08; TV-34 | AST-021; AST-020; AST-019; AST-031 | Backup & Recovery | IT Manager | Backup admin compromise, ransomware, failed restoration, process failure | Immutability/offline protection is unconfirmed, restore testing is ad hoc and backup credentials remain high-value. | Separate backup account; cloud copy; alerts; scheduled backup jobs | Limited | 5 | 5 | 25 | Critical | Mitigate | A failed recovery path could turn a containable incident into a prolonged enterprise outage. | Enable immutable or logically isolated backups; use separate identity/MFA for backup admins; perform quarterly restore tests; document RTO/RPO evidence; monitor deletion/configuration changes; maintain offline recovery documentation. | Systems Administrator | 2026-10-31 | In Progress | 2 | 5 | 10 | High | Above Appetite | PR.IR; RC.RP; PR.AA; GV.OV | A.8.13; A.8.14; A.5.30; A.5.29 | AST-021/020/019/031; TV-08/34
R-07 | Legacy Infrastructure Exploitation | Legacy Active Directory, file-server and virtualization components could be exploited or abused to gain privileged access, move laterally and access sensitive files. | TV-31; TV-32 | AST-018; AST-019; AST-020; AST-031 | Legacy Infrastructure | IT Manager | Unpatched/legacy service exploitation, credential dumping, inherited permissions | Technical debt, broad permissions and limited monitoring remain in the legacy environment. | Backups; EDR/AV; domain authentication; server logs | Weak | 5 | 5 | 25 | Critical | Mitigate | Legacy infrastructure provides a concentrated ransomware and privilege-escalation pathway. | Develop decommission/migration plan; isolate legacy VLAN; patch or apply compensating hardening; remove obsolete protocols/accounts; recertify file permissions; forward logs to central monitoring. | Systems Administrator | 2026-12-15 | Not Started | 3 | 4 | 12 | High | Above Appetite | ID.RA; PR.PS; PR.AA; DE.CM | A.8.8; A.8.9; A.8.20; A.8.22; A.5.18 | AST-018/019/020/031; TV-31/32
R-08 | Remote Employee Endpoint Compromise | A remote or mobile employee endpoint could be compromised by malware or phishing, leading to credential theft, cloud compromise or loss of confidential business data. | TV-09; TV-10 | AST-009; AST-010; AST-023 | Endpoint Workforce | COO / IT Support Lead | Phishing, malicious download, lost/stolen device | Patch cadence, local-admin exceptions, encryption validation and remote-wipe/session-revocation procedures are inconsistent. | EDR/AV; device authentication; OneDrive; endpoint management | Moderate | 4 | 4 | 16 | Critical | Mitigate | The large hybrid workforce creates continuous endpoint exposure. | Validate full-disk encryption coverage; enforce patch compliance; remove local admin; configure remote wipe; document stolen-device response; enforce device compliance for cloud access. | IT Support Lead | 2026-11-30 | Not Started | 2 | 3 | 6 | Moderate | Near Appetite | PR.PS; PR.AA; PR.DS; RS.MI | A.8.1; A.8.7; A.8.8; A.6.7 | AST-009/010/023; TV-09/10
R-09 | Cloud File Sharing / Oversharing | Employees could expose confidential customer or internal files through permissive SharePoint/OneDrive sharing or anonymous links. | TV-13; TV-29 | AST-008; AST-028; AST-029; AST-030 | Cloud Collaboration / Information Protection | COO | Misconfigured sharing, accidental disclosure, valid-account misuse | External-sharing governance is not consistently enforced and user safeguards/monitoring are incomplete. | M365 permissions; audit logs; user training | Limited | 5 | 4 | 20 | Critical | Mitigate | Cloud sharing is common and could cause material confidentiality breaches. | Disable anonymous links by default; restrict external sharing to approved groups; deploy DLP/sensitivity labels; configure high-volume sharing/download alerts; train users and review external shares quarterly. | IT Security Analyst / Data Owners | 2026-11-15 | Not Started | 2 | 3 | 6 | Moderate | Near Appetite | PR.DS; PR.AA; DE.CM; GV.PO | A.5.12; A.5.14; A.8.12; A.8.15 | AST-008/028/029/030; TV-13/29
R-10 | Customer Data Exfiltration from CRM | A malicious insider or compromised CRM user could bulk-export customer information and move it to an unmanaged location. | TV-14; TV-28 | AST-006; AST-028; AST-009 | Customer Relationship Management | Sales Director | Bulk export, valid-account abuse, insider misuse | Broad export permissions, duplicate copies and fragmented monitoring increase exfiltration risk. | Application permissions; basic audit logs; endpoint protection | Limited | 4 | 4 | 16 | Critical | Mitigate | Customer data loss could damage client trust and create contractual or legal exposure. | Restrict export permissions; alert on large exports; review dormant/high-risk accounts; apply DLP to customer data; define approved export/storage process; recertify CRM access quarterly. | Sales Director / IT Security | 2026-11-30 | Not Started | 2 | 3 | 6 | Moderate | Near Appetite | PR.DS; PR.AA; DE.CM; GV.RR | A.5.15; A.5.18; A.8.12; A.8.16 | AST-006/028/009; TV-14/28
R-11 | HR Data Unauthorized Access or Modification | A compromised or misused HR account could expose, export or alter sensitive employee information. | TV-15 | AST-007; AST-029 | Human Resources | HR Manager | Valid-account misuse, excessive permissions, unauthorized export | Access-review documentation and secure export procedures are incomplete. | MFA for HR admins; vendor audit logs; HR permissions | Moderate | 4 | 4 | 16 | Critical | Mitigate | HR data is highly sensitive and unauthorized changes could affect employees and payroll processes. | Perform quarterly HR access review; restrict export capability; configure audit alerts for bulk downloads/role changes; document correction/recovery process. | HR Manager / Application Admin | 2026-11-30 | Not Started | 2 | 3 | 6 | Moderate | Near Appetite | PR.AA; PR.DS; DE.CM | A.5.15; A.5.18; A.8.12; A.8.15 | AST-007/029; TV-15
R-12 | Accounting System Integrity Compromise | An attacker or malicious insider could alter financial records, vendor details or transaction information in the accounting platform. | TV-16 | AST-005; AST-030; AST-004 | Financial Operations | Finance Manager | Compromised account, unauthorized data modification, insider misuse | Vendor logging has not been formally reviewed and change verification/segregation controls need stronger assurance. | Admin MFA; application audit trail; finance controls | Moderate | 4 | 5 | 20 | Critical | Mitigate | Integrity loss in financial records could cause fraud, reporting errors and financial loss. | Enforce role segregation; review privileged/accounting roles quarterly; alert on bank/vendor master changes; retain independent transaction audit trail; review vendor logging and assurance. | Finance Manager / App Admin | 2026-10-31 | In Progress | 2 | 4 | 8 | Moderate | Above Appetite | PR.AA; DE.CM; GV.RR | A.5.3; A.5.15; A.5.18; A.8.15 | AST-005/030/004; TV-16
R-13 | Firewall / VPN Exploitation | Internet-facing firewall or VPN vulnerabilities, weak configurations or stolen credentials could provide unauthorized access to the corporate network. | TV-18; TV-19; TV-20 | AST-013; AST-014; AST-017; AST-015 | Corporate Network & Remote Access | IT Manager | Public-facing exploit, configuration error, credential compromise | Firmware lifecycle, rule review and baseline management are inconsistent; some VPN accounts lack MFA. | Firewalls; config backups; VPN logs; MFA for most users | Limited | 5 | 5 | 25 | Critical | Mitigate | Perimeter compromise could enable direct network access and ransomware/lateral movement. | Establish monthly firmware/vulnerability review; require admin MFA; enforce VPN MFA for all accounts; quarterly firewall-rule recertification; standardized configuration baseline; centralize firewall/VPN logs. | Network Administrator | 2026-10-15 | In Progress | 2 | 4 | 8 | Moderate | Above Appetite | PR.PS; PR.AA; ID.RA; DE.CM | A.8.20; A.8.21; A.8.22; A.8.8; A.5.15 | AST-013/014/017/015; TV-18/19/20
R-14 | RMM / Managed IT Supply-Chain Compromise | Compromise or misuse of the remote monitoring platform or managed IT provider access could enable malicious commands or administrative access across many endpoints and network devices. | TV-22; TV-23 | AST-022; AST-035; AST-009; AST-012; AST-013 | IT Operations / Third-Party Access | IT Manager | Trusted relationship compromise, vendor account takeover, third-party insider misuse | RMM has broad control; vendor assurance, role permissions, contractual obligations and offboarding evidence need strengthening. | MFA for some vendor/IT accounts; vendor logs; EDR | Limited | 4 | 5 | 20 | Critical | Mitigate | Trusted remote-management access can scale a compromise rapidly across the enterprise. | Require vendor MFA for every technician; named accounts only; quarterly third-party access review; restrict RMM roles; review vendor security assurance; alert on mass remote actions; define immediate vendor offboarding. | IT Manager / Procurement | 2026-11-15 | Not Started | 2 | 4 | 8 | Moderate | Above Appetite | GV.SC; PR.AA; DE.CM; RS.MI | A.5.19; A.5.20; A.5.22; A.5.15; A.8.16 | AST-022/035/009/012/013; TV-22/23
R-15 | Critical SaaS Vendor Breach | A breach at a CRM, HR, accounting or other SaaS provider could expose company data or disrupt critical business processes. | TV-17; TV-24 | AST-005; AST-006; AST-007; AST-028; AST-029; AST-030 | Third-Party / Cloud Services | COO / Procurement | Supplier compromise, provider outage, control-plane incident | Vendor assurance, recovery evidence and ongoing supplier-risk review are inconsistent. | Vendor contracts; internal access controls; vendor backup/resilience | Moderate | 4 | 5 | 20 | Critical | Transfer | Significant risk remains with the provider; contracts and assurance should reduce/transfer portions of impact. | Implement annual critical-vendor review; obtain assurance reports; define breach notification and cooperation; verify backup/BCP; document exit/export plan; assess cyber-insurance/contract liability. | Procurement / IT Manager | 2026-12-15 | Not Started | 3 | 4 | 12 | High | Above Appetite | GV.SC; ID.RA; RC.RP; RS.CO | A.5.19; A.5.20; A.5.22; A.5.23 | AST-005/006/007/028/029/030; TV-17/24
R-16 | Public Website / CMS Compromise | A vulnerable CMS, plugin or administrator account could be exploited to deface the public website, steal inquiry data or redirect visitors. | TV-25 | AST-024; AST-025 | Public Website | Marketing Manager | Public-facing exploit, outdated CMS/plugin, admin takeover | Patching responsibility and web-form security ownership are unclear. | Managed hosting; CMS authentication; backups | Limited | 4 | 3 | 12 | High | Mitigate | Impact is primarily reputational and availability-related but can enable customer phishing or data exposure. | Assign patching responsibility; monthly CMS/plugin review; MFA for admins; web application firewall where practical; secure inquiry forms; test restoration; monitor file/content changes. | External Web Vendor / Marketing | 2026-11-30 | Not Started | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | PR.PS; ID.RA; DE.CM; RC.RP | A.8.8; A.8.20; A.8.16; A.8.25 | AST-024/025; TV-25
R-17 | Domain Registrar / DNS Takeover | Compromise of the domain registrar account could allow malicious DNS or mail-routing changes that disrupt services, intercept traffic or support fraud. | TV-26 | AST-025; AST-001; AST-024 | Domain / Internet Services | IT Manager | Registrar account takeover, phishing, recovery-contact abuse | Recovery contacts need validation and domain ownership is a concentrated dependency. | Registrar MFA; account logs | Moderate | 4 | 5 | 20 | Critical | Mitigate | Domain takeover can affect email, website availability and trust simultaneously. | Validate recovery contacts; use phishing-resistant MFA; lock registrar changes; enable DNS/domain change alerts; maintain documented emergency recovery process; review registrar access quarterly. | IT Manager | 2026-10-31 | Not Started | 1 | 5 | 5 | Moderate | Near Appetite | PR.AA; PR.PS; RC.RP | A.5.16; A.8.20; A.8.16; A.5.30 | AST-025/001/024; TV-26
R-18 | Security Monitoring Blind Spots | Fragmented logging and incomplete centralized monitoring could delay detection and investigation of account compromise, ransomware, vendor misuse or data exfiltration. | TV-04; TV-15; TV-18; TV-22; TV-28; TV-30 | AST-034; AST-001; AST-013; AST-014; AST-023 | Cybersecurity Monitoring & Response | IT Manager | Insufficient telemetry, unmonitored SaaS/legacy logs, unclear alert ownership | Critical SaaS, legacy servers and network logs are not fully integrated; alert escalation is informal. | M365 logs; firewall logs; EDR; pilot SIEM/log repository | Limited | 5 | 4 | 20 | Critical | Mitigate | Detection delay increases dwell time and raises impact across multiple risk scenarios. | Define required log sources/use cases; onboard M365, firewalls, VPN, EDR and critical servers; set retention; establish alert ownership/severity/escalation; test detection scenarios quarterly. | IT Security Analyst | 2026-12-15 | Not Started | 3 | 3 | 9 | Moderate | Near Appetite | DE.CM; DE.AE; RS.AN; GV.OV | A.8.15; A.8.16; A.5.24; A.5.25 | AST-034/001/013/014/023; multiple Threat Matrix scenarios
R-19 | Insider Data Exfiltration | An employee or contractor with legitimate access could intentionally export customer, financial or other confidential information before departure or for personal gain. | TV-28 | AST-006; AST-008; AST-028; AST-030; AST-009 | Information Protection / Workforce | COO / HR Manager | Bulk exports, cloud sharing, removable media, valid-account misuse | Broad export/sharing permissions and limited behavioral monitoring make unusual data movement difficult to detect. | Application logs; endpoint protection; access controls | Limited | 3 | 5 | 15 | High | Mitigate | Though less frequent, insider theft could create significant commercial and confidentiality impact. | Formalize joiner/mover/leaver controls; restrict high-risk exports; DLP/alerting for bulk downloads; revoke access promptly; review access before/after notice period; document insider-risk escalation. | HR Manager / IT Security | 2026-12-15 | Not Started | 2 | 4 | 8 | Moderate | Near Appetite | PR.AA; PR.DS; DE.CM; GV.RR | A.5.18; A.6.5; A.8.12; A.8.16 | AST-006/008/028/030/009; TV-28
R-20 | Privileged Configuration Error | An authorized administrator could accidentally or intentionally make a change that weakens controls or disrupts identity, network or server services. | TV-30 | AST-012; AST-002; AST-013; AST-014; AST-020 | IT Change Management | IT Manager | Administrative error, unauthorized change, excessive privilege | Change-control evidence is limited and privileged administration is concentrated among a small IT team. | MFA; config backups; audit logs | Moderate | 3 | 5 | 15 | High | Mitigate | A single privileged error can cause enterprise-wide authentication or connectivity disruption. | Implement formal change approval for critical systems; peer review; emergency-change procedure; configuration versioning; role separation; periodic admin activity review. | IT Manager | 2026-11-30 | Not Started | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | GV.PO; GV.RR; PR.AA; DE.CM | A.5.3; A.5.15; A.8.9; A.8.32 | AST-012/002/013/014/020; TV-30
R-21 | Virtualization Host Single Point of Failure | Failure of the single virtualization host could make multiple legacy services unavailable until systems are repaired or restored. | TV-33 | AST-020; AST-018; AST-019 | Legacy Shared File Access | IT Manager | Hardware failure / infrastructure concentration | There is no clustered failover for the host supporting legacy services. | Backups; replacement hardware process | Limited | 4 | 4 | 16 | Critical | Mitigate | The failure would disrupt legacy authentication/file services but has a defined recovery path. | Evaluate migration to cloud/new platform; maintain tested host rebuild procedure; keep current configuration/image backups; pre-stage spare hardware or documented rapid replacement option. | Systems Administrator | 2026-12-31 | Not Started | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | PR.IR; RC.RP; GV.RM | A.8.14; A.5.30; A.8.13 | AST-020/018/019; TV-33
R-22 | Primary Internet Connectivity Outage | Failure of the Kingston primary internet circuit could interrupt access to cloud services, remote connectivity and normal head-office operations. | TV-27; TV-35 | AST-026; AST-013; AST-001; AST-017 | Corporate Network & Remote Access | COO / IT Manager | ISP outage, fiber cut, denial of service | The primary site has one principal circuit and failover capacity is limited. | Provider support; limited failover; branch/mobile alternatives | Moderate | 4 | 4 | 16 | Critical | Transfer | Availability risk is partly transferred to telecom providers but requires stronger redundancy. | Implement secondary diverse-path internet circuit or higher-capacity failover; test failover quarterly; document remote-work continuity; monitor ISP SLA performance. | COO / IT Manager | 2026-12-31 | Not Started | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | GV.SC; PR.IR; RC.RP | A.5.19; A.5.30; A.8.14 | AST-026/013/001/017; TV-27/35

## Top Risks
Top Enterprise Cybersecurity Risks
Rank | Risk ID | Risk | Inherent | Residual | Owner | Primary Treatment | Target
1 | R-03 | Cloud Account Compromise from Incomplete MFA | 25 Critical | 8 Moderate | IT Manager | Enforce universal MFA / conditional access | 2026-09-15
2 | R-04 | Privileged Identity / Administrator Takeover | 25 Critical | 10 High | IT Manager | Privileged access governance / hardened admin | 2026-10-31
3 | R-05 | Ransomware / Enterprise File Encryption | 25 Critical | 15 High | IT Manager | Endpoint/legacy hardening + segmentation | 2026-11-15
4 | R-06 | Backup Compromise / Recovery Failure | 25 Critical | 10 High | IT Manager | Immutable backups + restore testing | 2026-10-31
5 | R-07 | Legacy Infrastructure Exploitation | 25 Critical | 12 High | IT Manager | Legacy isolation / migration / hardening | 2026-12-15
6 | R-13 | Firewall / VPN Exploitation | 25 Critical | 8 Moderate | IT Manager | Patch, MFA, rule review, logging | 2026-10-15
7 | R-01 | Business Email Compromise / Payment Fraud | 25 Critical | 10 High | Finance Manager | Payment verification + anti-impersonation | 2026-09-30
8 | R-14 | RMM / Managed IT Supply-Chain Compromise | 20 Critical | 8 Moderate | IT Manager | Vendor MFA / access review / assurance | 2026-11-15
9 | R-15 | Critical SaaS Vendor Breach | 20 Critical | 12 High | COO / Procurement | Vendor assurance / contract / exit plan | 2026-12-15
10 | R-12 | Accounting System Integrity Compromise | 20 Critical | 8 Moderate | Finance Manager | SoD + bank/vendor change controls | 2026-10-31

## Risk Matrix
5 × 5 Enterprise Risk Matrix | [5 empty] | Inherent Risk Counts
Impact → | 1 | 2 | 3 | 4 | 5 | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25 | 5 | 0 | 0 | 0 | 2 | 7
4 | 4 | 8 | 12 | 16 | 20 | 4 | 0 | 0 | 1 | 5 | 5
3 | 3 | 6 | 9 | 12 | 15 | 3 | 0 | 0 | 0 | 0 | 2
2 | 2 | 4 | 6 | 8 | 10 | 2 | 0 | 0 | 0 | 0 | 0
1 | 1 | 2 | 3 | 4 | 5 | 1 | 0 | 0 | 0 | 0 | 0
Residual Risk Counts
[6 empty] | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
[6 empty] | 5 | 0 | 0 | 0 | 0 | 0
[6 empty] | 4 | 0 | 0 | 0 | 0 | 0
[6 empty] | 3 | 0 | 0 | 1 | 2 | 1
[6 empty] | 2 | 0 | 0 | 8 | 6 | 3
[6 empty] | 1 | 0 | 0 | 0 | 0 | 1

## Risk Criteria
Enterprise Risk Scoring Criteria
Likelihood | Rating | Guidance | Impact | Rating | Guidance
1 | Rare | Highly unlikely; strong controls and little exposure. | 1 | Insignificant | Minimal operational, financial or information-security impact.
2 | Unlikely | Possible but not expected; limited attack opportunity. | 2 | Minor | Contained disruption or limited exposure with straightforward recovery.
3 | Possible | Could reasonably occur in the assessment period. | 3 | Moderate | Material departmental disruption, moderate loss or confidential-data impact.
4 | Likely | Common threat pattern or recurring exposure makes occurrence credible. | 4 | Major | Serious business interruption, significant loss, major data exposure or reputational impact.
5 | Almost Certain | Frequent threat, direct exposure, major control gap or active attack pattern. | 5 | Severe | Enterprise-wide outage, major fraud, destructive compromise or severe loss of critical information/services.
Score | Rating | Management Response | Risk Appetite Interpretation
1–4 | Low | Normally accept/manage through standard controls and monitoring. | For this fictional organization: • Critical inherent/residual risks are above appetite and require active treatment or explicit senior-level acceptance. • High residual risks are normally above appetite and require time-bound remediation. • Moderate residual risks may be tolerated when controls are documented, owners accept accountability and monitoring exists. • Low residual risks are generally within tolerance. This appetite statement is a portfolio assumption, not a real company's board-approved risk appetite.
5–9 | Moderate | Manage within business area; document controls and monitor.
10–15 | High | Formal treatment plan and accountable owner required.
16–25 | Critical | Priority treatment; senior management oversight; do not accept without explicit decision.
Inherent vs. Residual Risk
Inherent risk reflects the assessed likelihood and impact before considering the effectiveness of existing controls. Residual risk reflects the risk expected to remain after the documented existing and proposed treatment controls are operating as intended. Residual likelihood and impact are analyst judgments, while the score itself is formula-driven (Likelihood × Impact). The register intentionally keeps impact high for several crown-jewel risks because strong controls can reduce probability without eliminating the business consequences if a severe event still occurs.

## Treatment Plan
Action ID | Risk ID | Priority | Treatment Action | Action Owner | Target Date | Status | Expected Control Outcome | Success Measure / Evidence | Dependencies | Notes
A-01 | R-03 | Critical | Enforce MFA across all cloud and VPN user accounts; disable legacy authentication and remove MFA exemptions. | Systems Administrator | 2026-09-15 | In Progress | Strong authentication coverage | 100% interactive users protected by MFA; exemption register empty or formally approved. | Entra/VPN policy changes | Immediate priority due to direct initial-access exposure.
A-02 | R-01 | Critical | Implement dual verification and independent callback for vendor-bank/payment detail changes. | Finance Manager | 2026-09-30 | In Progress | Reduced BEC/fraud likelihood | Documented procedure; sampled changes show independent verification evidence. | Finance process owners | Non-technical control with major fraud-reduction value.
A-03 | R-13 | Critical | Bring firewalls/VPN to approved firmware baseline, require admin/user MFA and complete firewall-rule recertification. | Network Administrator | 2026-10-15 | In Progress | Hardened perimeter and remote access | Current firmware; 100% VPN MFA; signed quarterly rule review. | Maintenance window / vendor support | Covers Kingston and Montego Bay devices.
A-04 | R-06 | Critical | Enable immutable/isolated backup copies and conduct documented restore tests. | Systems Administrator | 2026-10-31 | In Progress | Trusted ransomware recovery | Quarterly successful restore evidence; backup admin identity separate; immutable retention enabled. | Backup platform capabilities | Required before ransomware residual risk can be lowered further.
A-05 | R-04 | Critical | Implement privileged-access governance: quarterly recertification, separate admin accounts, hardened admin workstations/profiles and complete vault adoption. | IT Manager | 2026-10-31 | Not Started | Reduced privileged compromise exposure | All admin accounts inventoried; zero legacy secrets outside vault; review signed; hardened admin access in use. | Staff time / endpoint configuration | Enterprise-wide control improvement.
A-06 | R-12 | High | Strengthen accounting segregation of duties and alert on bank/vendor master changes. | Finance Manager | 2026-10-31 | In Progress | Financial-record integrity protection | Role matrix approved; bank/vendor changes produce auditable approval/alert. | Accounting SaaS features | Pairs with payment-verification control.
A-07 | R-02 | High | Deploy phishing-resistant MFA and executive-specific anti-phishing/conditional-access policies. | IT Security Analyst | 2026-10-15 | Not Started | Executive identity hardening | Executives enrolled in approved method; impersonation policies tested; risky sign-in alerts routed. | Licensing / training | Targeted crown-jewel identity protection.
A-08 | R-05 | High | Standardize endpoint/server patch SLA, remove local-admin exceptions and segment legacy servers. | IT Security / Systems Admin | 2026-11-15 | Not Started | Reduced ransomware/lateral-movement exposure | Patch compliance >95%; exceptions approved; segmentation validated; local-admin list minimized. | Change windows | Technical dependency for R-07 as well.
A-09 | R-14 | High | Perform RMM/MSP supplier risk review and restrict third-party privileged access. | IT Manager / Procurement | 2026-11-15 | Not Started | Controlled trusted-relationship access | Named accounts, MFA, role limits, quarterly access review and current vendor assurance evidence. | Vendor cooperation | High-impact supply-chain control.
A-10 | R-09 | High | Restrict SharePoint external sharing and deploy DLP/sensitivity controls for confidential data. | IT Security Analyst | 2026-11-15 | Not Started | Reduced accidental cloud data leakage | Anonymous links disabled; DLP policy active; external share review completed. | M365 licensing / data-owner input | Also supports R-10/R-19.
A-11 | R-08 | High | Validate endpoint encryption, remote wipe and device-compliance enforcement. | IT Support Lead | 2026-11-30 | Not Started | Protected hybrid workforce | Encryption dashboard shows >98% coverage; remote wipe tested; noncompliant devices blocked. | Endpoint management configuration | Focus on laptops used remotely.
A-12 | R-18 | High | Expand centralized security logging and define alert ownership/escalation. | IT Security Analyst | 2026-12-15 | Not Started | Improved detection and investigation | M365, firewall, VPN, EDR and critical server logs centralized; severity matrix and on-call ownership approved. | Log platform capacity | Cross-cutting control for many risks.
A-13 | R-07 | High | Create legacy-service migration/decommission plan and isolate remaining legacy systems. | IT Manager | 2026-12-15 | Not Started | Reduced legacy attack surface | Approved roadmap; obsolete protocols/accounts removed; network isolation validated. | Business application migration | May span multiple quarters.
A-14 | R-15 | High | Establish annual critical-SaaS/vendor assurance review and minimum contract security requirements. | Procurement / IT Manager | 2026-12-15 | Not Started | Improved supplier governance | Critical vendor list; assurance evidence; breach/BCP/exit clauses reviewed annually. | Procurement/legal review | Supports third-party residual-risk decisions.

## References
Source | Use in Workbook | URL | Status
NIST Cybersecurity Framework 2.0 | Primary framework for cybersecurity risk governance, prioritization and control-outcome mapping. | https://www.nist.gov/cyberframework | Current final CSF 2.0 framework
NIST SP 800-30 Rev. 1 — Guide for Conducting Risk Assessments | Supporting methodology for threat sources, vulnerabilities, likelihood, impact and risk analysis. | https://csrc.nist.gov/pubs/sp/800/30/r1/final | Final; NIST page updated 2026
NIST SP 1308 — CSF 2.0: Cybersecurity, Enterprise Risk Management, and Workforce Management Quick-Start Guide | Supporting enterprise-level cyber-risk communication and risk-register context. | https://www.nist.gov/publications/nist-cybersecurity-framework-20-cybersecurity-enterprise-risk-management-and-workforce | Published March 2026
ISO/IEC 27001:2022 | Supporting information-security control crosswalk. Included as a reference only; no certification claim is made. | https://www.iso.org/standard/27001 | Edition 3, 2022
Portfolio Disclaimer
This workbook is a simulated professional cybersecurity risk assessment for a fictional Jamaican company. Risk statements, likelihood/impact scores, assets, owners, dates, controls and residual-risk judgments are illustrative. NIST and ISO references are supporting framework mappings only. The workbook does not represent certification, regulatory approval, or a real organization's risk position.

## Lists
Treatment | Status | Score | Priority | Control Effectiveness
Mitigate | Not Started | 1 | Critical | Strong
Transfer | In Progress | 2 | High | Moderate
Avoid | Implemented | 3 | Medium | Limited
Accept | Accepted | 4 | Low | Weak
| Blocked | 5

## Management Dashboard
Enterprise Cybersecurity Risk — Executive Dashboard
IslandLink Business Services Ltd. (Fictional) ¦ Management View ¦ 26 August 2026
Enterprise Risks |  | Critical Inherent |  | High/Critical Residual |  | Exposure Reduction
22 |  | 19 |  | 6 |  | 59.04%
Above Appetite |  | Risks Improved |  | Actions In Progress |  | Next Critical Deadline
11 |  | 22 |  | 5 |  | 2026-09-15
Executive Interpretation
The current risk profile is dominated by identity, privileged access, ransomware/recovery, financial fraud, perimeter security and supplier risk. Planned treatment materially reduces the modeled aggregate exposure and eliminates Critical residual ratings, but several crown-jewel risks remain High because their business impact stays severe even after probability is reduced. Management attention should remain focused on universal MFA, payment verification, firewall/VPN hardening, immutable recovery, privileged-access governance, ransomware containment and supplier controls.
Inherent Rating | Count | Share |  | Residual Rating | Count | Share
Low | 0 | 0% |  | Low | 0 | 0%
Moderate | 0 | 0% |  | Moderate | 16 | 72.73%
High | 3 | 13.64% |  | High | 6 | 27.27%
Critical | 19 | 86.36% |  | Critical | 0 | 0%
Risk Appetite Position |  |  |  | Treatment Action Status
Above Appetite | 11 |  |  | Not Started | 9
Near Appetite | 7 |  |  | In Progress | 5
Within Tolerance with Treatment | 4 |  |  | Implemented | 0
Other / Unclassified | 0 |  |  | Accepted | 0
Top Residual Risks Requiring Management Attention
Rank | Risk ID | Risk | Residual Score | Rating | Owner | Target | Status
1 | R-05 | Ransomware / Enterprise File Encryption | 15 | High | IT Manager | 2026-11-15 | Not Started
2 | R-07 | Legacy Infrastructure Exploitation | 12 | High | IT Manager | 2026-12-15 | Not Started
3 | R-15 | Critical SaaS Vendor Breach | 12 | High | COO / Procurement | 2026-12-15 | Not Started
4 | R-04 | Privileged Identity / Administrator Takeover | 10 | High | IT Manager | 2026-10-31 | Not Started
5 | R-06 | Backup Compromise / Recovery Failure | 10 | High | IT Manager | 2026-10-31 | In Progress
6 | R-01 | Business Email Compromise / Payment Fraud | 10 | High | Finance Manager | 2026-09-30 | In Progress
7 | R-02 | Executive Account Compromise | 8 | Moderate | CEO / IT Manager | 2026-10-15 | Not Started
8 | R-03 | Cloud Account Compromise from Incomplete MFA | 8 | Moderate | IT Manager | 2026-09-15 | In Progress
9 | R-12 | Accounting System Integrity Compromise | 8 | Moderate | Finance Manager | 2026-10-31 | In Progress
10 | R-13 | Firewall / VPN Exploitation | 8 | Moderate | IT Manager | 2026-10-15 | In Progress

## Heatmap Dashboard
Inherent vs. Residual Risk Heatmaps
Counts show how many enterprise risks occupy each likelihood × impact position.
INHERENT RISK | [6 empty] | RESIDUAL RISK
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5 |  | Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 2 | 7 |  | 5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 1 | 5 | 5 |  | 4 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 2 |  | 3 | 0 | 0 | 1 | 2 | 1
2 | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 8 | 6 | 3
1 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 1
Risk Rating Legend
Low (1–4) |  |  | Moderate (5–9) |  |  | High (10–15) |  |  | Critical (16–25)
Risk Movement Summary |  |  |  | Residual High Risks
Movement | Count | Meaning |  | Risk ID | Risk | Score | Owner | Appetite
Improved | 22 | Residual rating is lower than inherent rating. |  | R-01 | Business Email Compromise / Payment Fraud | 10 | Finance Manager | Above Appetite
Unchanged | 0 | Risk remains in the same rating band. |  | R-04 | Privileged Identity / Administrator Takeover | 10 | IT Manager | Above Appetite
Worsened | 0 | Residual rating is higher than inherent rating (should be investigated). |  | R-05 | Ransomware / Enterprise File Encryption | 15 | IT Manager | Above Appetite
|  |  |  | R-06 | Backup Compromise / Recovery Failure | 10 | IT Manager | Above Appetite
|  |  |  | R-07 | Legacy Infrastructure Exploitation | 12 | IT Manager | Above Appetite
|  |  |  | R-15 | Critical SaaS Vendor Breach | 12 | COO / Procurement | Above Appetite

## Risk Movement
Risk Treatment Effectiveness — Inherent vs. Residual
Top enterprise risks and modeled exposure after proposed treatment controls.
Total Inherent Exposure |  | Total Residual Exposure |  | Exposure Reduced |  | Risks with Lower Rating
437 |  | 179 |  | 59.04% |  | 22
Rank | Risk ID | Risk Title | Inherent Score | Residual Score | Reduction | Residual Rating
1 | R-03 | Cloud Account Compromise from Incomplete MFA | 25 | 8 | 17 | Moderate
2 | R-04 | Privileged Identity / Administrator Takeover | 25 | 10 | 15 | High
3 | R-05 | Ransomware / Enterprise File Encryption | 25 | 15 | 10 | High
4 | R-06 | Backup Compromise / Recovery Failure | 25 | 10 | 15 | High
5 | R-07 | Legacy Infrastructure Exploitation | 25 | 12 | 13 | High
6 | R-13 | Firewall / VPN Exploitation | 25 | 8 | 17 | Moderate
7 | R-01 | Business Email Compromise / Payment Fraud | 25 | 10 | 15 | High
8 | R-14 | RMM / Managed IT Supply-Chain Compromise | 20 | 8 | 12 | Moderate
9 | R-15 | Critical SaaS Vendor Breach | 20 | 12 | 8 | High
10 | R-12 | Accounting System Integrity Compromise | 20 | 8 | 12 | Moderate

## Ownership & Actions
Risk Ownership & Remediation Delivery
Accountability view for enterprise risks and treatment actions.
Risk Owner | Total Risks | High/Critical Residual | Above Appetite |  | Treatment Action Status
IT Manager | 11 | 4 | 7 |  | Status | Count
Finance Manager | 2 | 1 | 2 |  | Not Started | 9
CEO / IT Manager | 1 | 0 | 1 |  | In Progress | 5
COO / IT Support Lead | 1 | 0 | 0 |  | Implemented | 0
COO | 1 | 0 | 0 |  | Blocked | 0
Sales Director | 1 | 0 | 0
HR Manager | 1 | 0 | 0
COO / Procurement | 1 | 1 | 1 |  | Upcoming Action Deadlines
Marketing Manager | 1 | 0 | 0 |  | Window | Open Actions | 2026-08-26
COO / HR Manager | 1 | 0 | 0 |  | Due within 30 days | 1
COO / IT Manager | 1 | 0 | 0 |  | Due within 60 days | 3
[5 empty] | Due within 90 days | 6
[5 empty] | Due after 90 days | 4
Critical / High Treatment Actions
Action | Risk | Priority | Owner | Due | Status | Outcome | Evidence
A-01 | R-03 | Critical | Systems Administrator | 2026-09-15 | In Progress | Strong authentication coverage | 100% interactive users protected by MFA; exemption register empty or formally approved.
A-02 | R-01 | Critical | Finance Manager | 2026-09-30 | In Progress | Reduced BEC/fraud likelihood | Documented procedure; sampled changes show independent verification evidence.
A-03 | R-13 | Critical | Network Administrator | 2026-10-15 | In Progress | Hardened perimeter and remote access | Current firmware; 100% VPN MFA; signed quarterly rule review.
A-04 | R-06 | Critical | Systems Administrator | 2026-10-31 | In Progress | Trusted ransomware recovery | Quarterly successful restore evidence; backup admin identity separate; immutable retention enabled.
A-05 | R-04 | Critical | IT Manager | 2026-10-31 | Not Started | Reduced privileged compromise exposure | All admin accounts inventoried; zero legacy secrets outside vault; review signed; hardened admin access in use.
A-06 | R-12 | High | Finance Manager | 2026-10-31 | In Progress | Financial-record integrity protection | Role matrix approved; bank/vendor changes produce auditable approval/alert.
A-07 | R-02 | High | IT Security Analyst | 2026-10-15 | Not Started | Executive identity hardening | Executives enrolled in approved method; impersonation policies tested; risky sign-in alerts routed.
A-08 | R-05 | High | IT Security / Systems Admin | 2026-11-15 | Not Started | Reduced ransomware/lateral-movement exposure | Patch compliance >95%; exceptions approved; segmentation validated; local-admin list minimized.
A-09 | R-14 | High | IT Manager / Procurement | 2026-11-15 | Not Started | Controlled trusted-relationship access | Named accounts, MFA, role limits, quarterly access review and current vendor assurance evidence.
A-10 | R-09 | High | IT Security Analyst | 2026-11-15 | Not Started | Reduced accidental cloud data leakage | Anonymous links disabled; DLP policy active; external share review completed.
A-11 | R-08 | High | IT Support Lead | 2026-11-30 | Not Started | Protected hybrid workforce | Encryption dashboard shows >98% coverage; remote wipe tested; noncompliant devices blocked.
A-12 | R-18 | High | IT Security Analyst | 2026-12-15 | Not Started | Improved detection and investigation | M365, firewall, VPN, EDR and critical server logs centralized; severity matrix and on-call ownership approved.
A-13 | R-07 | High | IT Manager | 2026-12-15 | Not Started | Reduced legacy attack surface | Approved roadmap; obsolete protocols/accounts removed; network isolation validated.
A-14 | R-15 | High | Procurement / IT Manager | 2026-12-15 | Not Started | Improved supplier governance | Critical vendor list; assurance evidence; breach/BCP/exit clauses reviewed annually.

## Dashboard Data
Risk ID | Risk Title | Risk Owner | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Appetite Position | Target Date | Status | Inherent Rank | Residual Rank | Rating Change | Rank | Risk ID | Risk Title | Inherent Score | Residual Score | Residual Rating | Owner
R-01 | Business Email Compromise / Payment Fraud | Finance Manager | 5 | 5 | 25 | Critical | 2 | 5 | 10 | High | Above Appetite | 2026-09-30 | In Progress | 4 | 3 | 1 | 1 | R-03 | Cloud Account Compromise from Incomplete MFA | 25 | 8 | Moderate | IT Manager
R-02 | Executive Account Compromise | CEO / IT Manager | 4 | 5 | 20 | Critical | 2 | 4 | 8 | Moderate | Above Appetite | 2026-10-15 | Not Started | 4 | 2 | 2 | 2 | R-04 | Privileged Identity / Administrator Takeover | 25 | 10 | High | IT Manager
R-03 | Cloud Account Compromise from Incomplete MFA | IT Manager | 5 | 5 | 25 | Critical | 2 | 4 | 8 | Moderate | Above Appetite | 2026-09-15 | In Progress | 4 | 2 | 2 | 3 | R-05 | Ransomware / Enterprise File Encryption | 25 | 15 | High | IT Manager
R-04 | Privileged Identity / Administrator Takeover | IT Manager | 5 | 5 | 25 | Critical | 2 | 5 | 10 | High | Above Appetite | 2026-10-31 | Not Started | 4 | 3 | 1 | 4 | R-06 | Backup Compromise / Recovery Failure | 25 | 10 | High | IT Manager
R-05 | Ransomware / Enterprise File Encryption | IT Manager | 5 | 5 | 25 | Critical | 3 | 5 | 15 | High | Above Appetite | 2026-11-15 | Not Started | 4 | 3 | 1 | 5 | R-07 | Legacy Infrastructure Exploitation | 25 | 12 | High | IT Manager
R-06 | Backup Compromise / Recovery Failure | IT Manager | 5 | 5 | 25 | Critical | 2 | 5 | 10 | High | Above Appetite | 2026-10-31 | In Progress | 4 | 3 | 1 | 6 | R-13 | Firewall / VPN Exploitation | 25 | 8 | Moderate | IT Manager
R-07 | Legacy Infrastructure Exploitation | IT Manager | 5 | 5 | 25 | Critical | 3 | 4 | 12 | High | Above Appetite | 2026-12-15 | Not Started | 4 | 3 | 1 | 7 | R-01 | Business Email Compromise / Payment Fraud | 25 | 10 | High | Finance Manager
R-08 | Remote Employee Endpoint Compromise | COO / IT Support Lead | 4 | 4 | 16 | Critical | 2 | 3 | 6 | Moderate | Near Appetite | 2026-11-30 | Not Started | 4 | 2 | 2 | 8 | R-14 | RMM / Managed IT Supply-Chain Compromise | 20 | 8 | Moderate | IT Manager
R-09 | Cloud File Sharing / Oversharing | COO | 5 | 4 | 20 | Critical | 2 | 3 | 6 | Moderate | Near Appetite | 2026-11-15 | Not Started | 4 | 2 | 2 | 9 | R-15 | Critical SaaS Vendor Breach | 20 | 12 | High | COO / Procurement
R-10 | Customer Data Exfiltration from CRM | Sales Director | 4 | 4 | 16 | Critical | 2 | 3 | 6 | Moderate | Near Appetite | 2026-11-30 | Not Started | 4 | 2 | 2 | 10 | R-12 | Accounting System Integrity Compromise | 20 | 8 | Moderate | Finance Manager
R-11 | HR Data Unauthorized Access or Modification | HR Manager | 4 | 4 | 16 | Critical | 2 | 3 | 6 | Moderate | Near Appetite | 2026-11-30 | Not Started | 4 | 2 | 2
R-12 | Accounting System Integrity Compromise | Finance Manager | 4 | 5 | 20 | Critical | 2 | 4 | 8 | Moderate | Above Appetite | 2026-10-31 | In Progress | 4 | 2 | 2
R-13 | Firewall / VPN Exploitation | IT Manager | 5 | 5 | 25 | Critical | 2 | 4 | 8 | Moderate | Above Appetite | 2026-10-15 | In Progress | 4 | 2 | 2
R-14 | RMM / Managed IT Supply-Chain Compromise | IT Manager | 4 | 5 | 20 | Critical | 2 | 4 | 8 | Moderate | Above Appetite | 2026-11-15 | Not Started | 4 | 2 | 2
R-15 | Critical SaaS Vendor Breach | COO / Procurement | 4 | 5 | 20 | Critical | 3 | 4 | 12 | High | Above Appetite | 2026-12-15 | Not Started | 4 | 3 | 1
R-16 | Public Website / CMS Compromise | Marketing Manager | 4 | 3 | 12 | High | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | 2026-11-30 | Not Started | 3 | 2 | 1
R-17 | Domain Registrar / DNS Takeover | IT Manager | 4 | 5 | 20 | Critical | 1 | 5 | 5 | Moderate | Near Appetite | 2026-10-31 | Not Started | 4 | 2 | 2
R-18 | Security Monitoring Blind Spots | IT Manager | 5 | 4 | 20 | Critical | 3 | 3 | 9 | Moderate | Near Appetite | 2026-12-15 | Not Started | 4 | 2 | 2
R-19 | Insider Data Exfiltration | COO / HR Manager | 3 | 5 | 15 | High | 2 | 4 | 8 | Moderate | Near Appetite | 2026-12-15 | Not Started | 3 | 2 | 1
R-20 | Privileged Configuration Error | IT Manager | 3 | 5 | 15 | High | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | 2026-11-30 | Not Started | 3 | 2 | 1
R-21 | Virtualization Host Single Point of Failure | IT Manager | 4 | 4 | 16 | Critical | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | 2026-12-31 | Not Started | 4 | 2 | 2
R-22 | Primary Internet Connectivity Outage | COO / IT Manager | 4 | 4 | 16 | Critical | 2 | 3 | 6 | Moderate | Within Tolerance with Treatment | 2026-12-31 | Not Started | 4 | 2 | 2