## Executive Dashboard
Cybersecurity Risk Treatment — Executive Dashboard
IslandLink Business Services Ltd. (Fictional) ¦ Assessment Date: 26 August 2026
Treatment Actions |  | Critical / High |  | In Progress |  | Effort-Weighted Progress
18 |  | 15 |  | 6 |  | 10.32%
Total Effort |  | Due ≤30 Days |  | Blocked / Overdue |  | Year-End Actions
252 |  | 1 |  | 0 |  | 18
Executive Treatment Strategy
The treatment plan prioritizes rapid closure of credential-based entry paths, financial fraud controls, perimeter weaknesses and recovery risk before shifting into broader platform hardening, monitoring, incident readiness, supplier governance and data protection. The first 60 days focus on controls that materially change exposure for the highest-risk crown jewels. Later workstreams establish sustainable detection, governance and resilience. Residual risk should only be re-scored after evidence demonstrates that each treatment is operating effectively.
Priority | Actions | Effort Days |  | Status | Actions | Effort Days
Critical | 6 | 62 |  | Not Started | 12 | 200
High | 9 | 158 |  | In Progress | 6 | 52
Medium | 3 | 32 |  | Implemented | 0 | 0
Low | 0 | 0 |  | Blocked | 0 | 0
Immediate Management Priorities
Order | Action ID | Action | Priority | Owner | Due | Status | Evidence
1 | TP-01 | Enforce MFA for all Microsoft 365, SaaS and VPN accounts; disable legacy authentication and remove unjustified MFA exemptions. | Critical | IT Manager | 2026-09-15 | In Progress | Partial
2 | TP-02 | Implement independent callback/dual verification for vendor-bank and payment-detail changes; strengthen finance anti-impersonation protections. | Critical | Finance Manager | 2026-09-30 | In Progress | Partial
3 | TP-05 | Upgrade Kingston/Montego Bay firewalls and VPN to approved firmware, enforce administrative/user MFA, recertify rules and centralize perimeter logs. | Critical | IT Manager | 2026-10-15 | In Progress | Partial
4 | TP-04 | Enable immutable or logically isolated backups, separate backup administrator identities and execute documented restore tests. | Critical | IT Manager | 2026-10-31 | In Progress | Partial
5 | TP-13 | Approve cyber risk appetite/tolerance and establish quarterly management review of top risks, treatment progress, overdue actions and risk acceptance. | Critical | COO / Executive Team | 2026-10-31 | In Progress | Partial
6 | TP-03 | Implement privileged-access governance: separate administrator identities, quarterly recertification, central vault adoption and hardened administrator workstations/profiles. | Critical | IT Manager | 2026-10-31 | Not Started | Planned
7 | TP-06 | Establish patch and secure-configuration SLA, remove unnecessary local administrator rights and remediate critical endpoint/server exceptions. | High | IT Manager | 2026-11-30 | Not Started | Planned
8 | TP-08 | Centralize priority telemetry from M365, VPN, firewalls, EDR and critical servers; define detection use cases, alert severity, ownership and escalation. | High | IT Manager | 2026-12-15 | Not Started | Planned

## Risk Treatment Plan
Action ID | Workstream | Priority | Risk IDs | Treatment | CSF 2.0 Categories | Remediation Action | Business Rationale | Accountable Owner | Responsible Owner | Start Date | Target Date | Status | Completion % | Days Remaining | Schedule Flag | Estimated Effort (Person-Days) | Budget Tier | Key Dependencies | Success Criteria | Required Evidence | Evidence Status | Residual Risk Objective | Phase | Notes
TP-01 | Identity & Privileged Access | Critical | R-03; R-13 | Mitigate | PR.AA | Enforce MFA for all Microsoft 365, SaaS and VPN accounts; disable legacy authentication and remove unjustified MFA exemptions. | Closes a direct credential-based initial-access path affecting email, cloud data and remote network access. | IT Manager | Systems Administrator | 2026-08-27 | 2026-09-15 | In Progress | 50% | 20 | Due ≤30d | 8 | Low | Entra ID and VPN policy access; maintenance communication | 100% interactive workforce and VPN accounts protected by MFA; legacy authentication disabled; exceptions documented and approved. | MFA coverage export; conditional-access configuration; VPN authentication report | Partial | Reduce R-03/R-13 residual likelihood from 5 to 2 while retaining impact assumptions. | 0–30 Days | Immediate priority.
TP-02 | Financial Fraud Prevention | Critical | R-01; R-12 | Mitigate | PR.AA; PR.AT; DE.CM | Implement independent callback/dual verification for vendor-bank and payment-detail changes; strengthen finance anti-impersonation protections. | Reduces business email compromise and unauthorized accounting changes that could create direct financial loss. | Finance Manager | Finance Manager / IT Security | 2026-08-27 | 2026-09-30 | In Progress | 50% | 35 | Due 31–60d | 6 | Low | Finance procedure approval; M365 email-security configuration | 100% vendor-bank changes independently verified; anti-impersonation policy tested for finance/executives; audit sample shows dual approval. | Approved finance procedure; sampled verification records; anti-phishing configuration screenshots/export | Partial | Reduce R-01 residual likelihood to 2 and R-12 residual likelihood to 2. | 31–60 Days | High business-value non-technical control.
TP-03 | Identity & Privileged Access | Critical | R-04; R-20 | Mitigate | PR.AA; GV.RR | Implement privileged-access governance: separate administrator identities, quarterly recertification, central vault adoption and hardened administrator workstations/profiles. | Privileged account compromise can create enterprise-wide loss of control across identity, network, endpoints and backups. | IT Manager | IT Manager / Systems Administrator | 2026-09-01 | 2026-10-31 | Not Started | 0% | 66 | Due 61–90d | 18 | Medium | Endpoint configuration; password vault; administrator inventory | All privileged accounts inventoried; zero routine administration from standard identities; all legacy secrets vaulted; quarterly review completed. | Privileged-account register; access-review sign-off; vault report; hardened admin configuration evidence | Planned | Reduce R-04 residual likelihood to 2; keep severe impact at 5. | 31–60 Days | Cross-cutting control for multiple risks.
TP-04 | Resilience & Ransomware | Critical | R-05; R-06 | Mitigate | PR.IR; RC.RP | Enable immutable or logically isolated backups, separate backup administrator identities and execute documented restore tests. | Preserves the organization's trusted recovery path during ransomware, destructive attacks or infrastructure failure. | IT Manager | Systems Administrator | 2026-08-28 | 2026-10-31 | In Progress | 50% | 66 | Due 61–90d | 12 | Medium | Backup-platform capability; storage capacity; maintenance window | Immutable retention enabled; separate MFA-protected backup identity used; quarterly restore test succeeds within target RTO/RPO. | Backup configuration; restore-test report; recovery timing evidence; backup account review | Partial | Reduce R-06 residual likelihood to 2 and support lower ransomware recovery impact. | 31–60 Days | Must be validated, not assumed.
TP-05 | Network & Platform Security | Critical | R-13; R-05 | Mitigate | PR.PS; PR.AA; DE.CM | Upgrade Kingston/Montego Bay firewalls and VPN to approved firmware, enforce administrative/user MFA, recertify rules and centralize perimeter logs. | Protects the primary external boundary and reduces public-exploit, stolen-credential and misconfiguration exposure. | IT Manager | Network Administrator | 2026-08-28 | 2026-10-15 | In Progress | 50% | 50 | Due 31–60d | 10 | Medium | Vendor firmware; maintenance window; log repository | Current supported firmware; 100% VPN/admin MFA; signed rule review; configuration backup; logs visible in central monitoring. | Firmware/version evidence; VPN MFA report; signed rule-review sheet; centralized log sample | Partial | Reduce R-13 residual likelihood from 5 to 2. | 31–60 Days | Includes both office perimeter devices.
TP-06 | Network & Platform Security | High | R-05; R-07; R-08 | Mitigate | PR.PS | Establish patch and secure-configuration SLA, remove unnecessary local administrator rights and remediate critical endpoint/server exceptions. | Reduces malware execution, privilege escalation and ransomware lateral movement across the hybrid workforce. | IT Manager | IT Support Lead / Systems Administrator | 2026-09-15 | 2026-11-30 | Not Started | 0% | 96 | Due 90+d | 20 | Medium | Endpoint management tooling; application testing; maintenance windows | ≥95% critical/high patch compliance within SLA; local-admin exceptions approved; baseline deviations tracked and remediated. | Patch compliance dashboard; local-admin report; exception register; secure-baseline checklist | Planned | Reduce R-05/R-08 likelihood and constrain lateral movement. | 61–90 Days | Ongoing operating control after initial remediation.
TP-07 | Legacy Technology Reduction | High | R-05; R-07; R-21 | Mitigate | PR.PS; ID.IM; PR.IR | Isolate legacy Active Directory/file services, remove obsolete protocols/accounts and execute a phased migration/decommission plan. | Legacy technical debt creates ransomware, privilege escalation and single-point-of-failure exposure. | IT Manager | Systems Administrator | 2026-09-15 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 30 | High | Business migration plan; application compatibility; user communications | Legacy VLAN isolation validated; obsolete accounts/protocols removed; migration roadmap approved; priority data moved to supported platforms. | Network diagram; disabled-protocol/account report; migration plan; milestone evidence | Planned | Reduce R-07 residual likelihood to 3 and R-21 exposure through migration. | 90+ Days | Likely multi-quarter completion; first phase due December.
TP-08 | Detection & Response | High | R-18; R-04; R-05; R-14 | Mitigate | DE.CM; DE.AE | Centralize priority telemetry from M365, VPN, firewalls, EDR and critical servers; define detection use cases, alert severity, ownership and escalation. | Fragmented telemetry increases attacker dwell time and weakens incident scoping and evidence. | IT Manager | IT Security Analyst | 2026-09-15 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 22 | Medium | Log platform capacity; admin access to source systems; storage/retention budget | Priority log sources onboarded; alert severity matrix approved; defined detections tested; critical alerts assigned and handled within SLA. | Logging coverage matrix; alert catalog; test-alert evidence; retention configuration | Planned | Reduce R-18 likelihood/impact through earlier detection and investigation. | 90+ Days | Monitoring quality matters more than raw log volume.
TP-09 | Detection & Response | High | R-01; R-02; R-05; R-13; R-14; R-18 | Mitigate | RS.MA; RS.AN; RS.MI; RS.CO | Approve an incident response plan and build tested playbooks for BEC, compromised cloud account, ransomware, firewall/VPN compromise and vendor/RMM incidents. | Repeatable response reduces containment time, decision uncertainty and recovery impact during high-severity events. | IT Manager | IT Security Analyst / IT Manager | 2026-09-30 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 16 | Low | Executive participation; contact lists; logging improvements | IR plan approved; severity model defined; five playbooks completed; tabletop exercise held; lessons assigned to owners. | Approved IR plan; playbooks; tabletop attendance/results; lessons-learned tracker | Planned | Reduce response-related impact across R-01/R-02/R-05/R-13/R-14/R-18. | 90+ Days | Exercise at least annually and after major change.
TP-10 | Third-Party Risk | High | R-14; R-15; R-22 | Mitigate | GV.SC | Implement tiered vendor risk management for SaaS, RMM, MSP and telecom providers, including assurance evidence, contract requirements, access review and exit planning. | Trusted suppliers have privileged access or host critical data/services and can create systemic concentration risk. | COO / Procurement | Procurement / IT Manager | 2026-09-15 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 18 | Medium | Procurement support; vendor cooperation; contract review | Critical vendor register approved; assurance reviewed annually; minimum security clauses defined; privileged vendor access reviewed quarterly. | Vendor register; assurance reports; contract checklist; vendor-access review; exit-plan template | Planned | Reduce R-14 likelihood and transfer/reduce portions of R-15/R-22 impact. | 90+ Days | Focus first on RMM/MSP and critical SaaS.
TP-11 | Data Protection & Human Factors | High | R-09; R-10; R-11; R-19 | Mitigate | PR.DS; PR.AA | Restrict anonymous/external sharing, implement DLP/sensitivity labels, reduce bulk-export privileges and create quarterly data-access reviews. | Limits accidental and intentional loss of customer, employee and financial information. | COO | IT Security Analyst / Data Owners | 2026-09-30 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 18 | Medium | M365/SaaS licensing; data-owner participation; classification decisions | Anonymous links disabled by default; DLP rules active; bulk exports restricted/alerted; quarterly access/share review completed. | DLP policy export; external-sharing report; export-role matrix; quarterly review evidence | Planned | Reduce R-09/R-10/R-11/R-19 likelihood to 2 where feasible. | 90+ Days | Start with customer and HR datasets.
TP-12 | Data Protection & Human Factors | High | R-01; R-02; R-09; R-19 | Mitigate | PR.AT | Launch measured security-awareness program with quarterly phishing exercises and targeted finance, executive, administrator and data-owner modules. | Human-targeted attacks are common and require role-specific behaviors in addition to technical controls. | HR Manager | HR / IT Security | 2026-10-01 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 10 | Low | Training platform; employee time; communications | ≥95% annual training completion; quarterly phishing simulations; targeted modules completed; repeat-click rate trends downward. | Training completion report; phishing metrics; role-module attendance | Missing | Reduce phishing/social-engineering likelihood supporting R-01/R-02. | 90+ Days | Metrics should be used for improvement, not punishment.
TP-13 | Governance & Oversight | Critical | R-01 through R-22 | Mitigate | GV.RM; GV.OV | Approve cyber risk appetite/tolerance and establish quarterly management review of top risks, treatment progress, overdue actions and risk acceptance. | Creates senior-management accountability and a repeatable decision mechanism for enterprise cyber risk. | COO / Executive Team | IT Manager | 2026-09-01 | 2026-10-31 | In Progress | 50% | 66 | Due 61–90d | 8 | Low | Executive meeting cadence; management approval | Risk appetite statement approved; quarterly cyber-risk meeting scheduled; decisions/minutes maintained; overdue actions escalated. | Approved appetite statement; meeting minutes; dashboard pack; risk acceptance record | Partial | Ensure residual risks above appetite receive explicit treatment or acceptance. | 31–60 Days | Core GRC governance deliverable.
TP-14 | Governance & Oversight | High | R-03; R-08; R-09; R-13; R-20 | Mitigate | GV.PO; GV.RR | Approve a minimum cybersecurity policy suite and RACI covering access control, remote work, patching, backups, incident response, supplier security and change management. | Formal policy converts informal practices into repeatable, auditable requirements with clear accountability. | COO / IT Manager | IT Manager / HR | 2026-09-30 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 14 | Low | Management and HR review; policy owners | Core policy suite approved and communicated; named owners/review dates; cybersecurity RACI approved. | Approved policies; distribution/acknowledgment record; RACI | Missing | Reduce governance/control inconsistency across multiple risks. | 90+ Days | Policies should reflect actual operating capability.
TP-15 | Governance & Oversight | Medium | R-05; R-07; R-13; R-16 | Mitigate | ID.RA; ID.AM | Establish monthly vulnerability/threat review, formal risk reassessment triggers and quarterly asset-inventory reconciliation. | Keeps the risk register current as technology, vulnerabilities and business dependencies change. | IT Manager | IT Security Analyst | 2026-09-15 | 2026-11-30 | In Progress | 50% | 96 | Due 90+d | 8 | Low | Asset sources; vulnerability/threat inputs | Monthly vulnerability/threat review completed; risk register updated after major incidents/changes; asset inventory reconciled quarterly. | Review meeting record; vulnerability summary; updated risk/asset registers | Partial | Prevent risk decisions from becoming stale and support R-05/R-07/R-13/R-16. | 61–90 Days | Recurring governance activity.
TP-16 | Resilience & Ransomware | Medium | R-21; R-22 | Mitigate | PR.IR; RC.RP; RC.CO | Improve infrastructure continuity through secondary internet/failover testing, virtualization recovery procedures and business-service recovery communications. | Reduces single points of failure and helps restore prioritized services with clear stakeholder updates. | COO / IT Manager | Network Administrator / Systems Administrator | 2026-10-01 | 2026-12-31 | Not Started | 0% | 127 | Due 90+d | 16 | High | Telecom procurement; budget; recovery runbooks | Secondary connectivity solution approved/tested; host rebuild procedure validated; recovery communication template approved. | Failover-test result; recovery procedure; supplier SLA; recovery communications template | Planned | Reduce R-21/R-22 likelihood or outage duration. | 90+ Days | May require capital/telecom spend.
TP-17 | Endpoint & Data Security | High | R-08; R-19 | Mitigate | PR.PS; PR.DS | Validate full-disk encryption, enforce device compliance, configure remote wipe and formalize lost/stolen-device response. | Protects confidential data and authenticated cloud sessions for a hybrid and mobile workforce. | IT Manager | IT Support Lead | 2026-09-15 | 2026-11-30 | Not Started | 0% | 96 | Due 90+d | 10 | Low | Endpoint-management policy; device inventory | ≥98% managed laptops encrypted; non-compliant devices blocked from sensitive cloud access; remote-wipe test completed. | Encryption/compliance dashboard; remote-wipe test; lost-device response procedure | Planned | Reduce R-08 and physical-loss contribution to R-19. | 61–90 Days | Executive/finance laptops prioritized first.
TP-18 | Public & Domain Security | Medium | R-16; R-17 | Mitigate | PR.PS; PR.AA; RC.RP | Assign website patch ownership, enforce registrar/CMS MFA, enable change alerts and document emergency domain/website recovery. | Protects the company's public presence, email routing trust and customer-facing information channels. | IT Manager / Marketing Manager | External Web Vendor / IT Manager | 2026-10-01 | 2026-12-15 | Not Started | 0% | 111 | Due 90+d | 8 | Low | Registrar/web-vendor cooperation; CMS maintenance access | Supported CMS/plugins; MFA on registrar/CMS admins; DNS/domain alerts enabled; recovery contacts tested; restoration procedure documented. | CMS patch report; registrar MFA/change-alert evidence; recovery contact test; restore procedure | Planned | Reduce R-16/R-17 likelihood while preserving recoverability. | 90+ Days | Lower enterprise priority than identity/ransomware work.

## 30-60-90 Roadmap
30 / 60 / 90-Day Cyber Risk Remediation Roadmap
Roadmap anchored to assessment date: 26 August 2026
Phase | Objective | Priority Actions | Risk Outcomes | Primary Owners | End Date | Success Gate | Management Decision
0–30 Days | Close the easiest high-impact entry paths and establish management control. | TP-01 Universal MFA; begin TP-02 payment verification; begin TP-04 immutable recovery; begin TP-05 perimeter hardening; start TP-13 risk governance. | Reduce immediate credential, BEC, VPN and ransomware-recovery exposure. | IT Manager; Finance Manager; COO | 2026-09-25 | Universal MFA substantially complete; finance callback procedure operating; backup/perimeter implementation underway; risk appetite draft ready. | Confirm no unmanaged critical authentication exceptions remain.
31–60 Days | Harden privileged access, financial integrity, perimeter controls and recovery. | Complete TP-02; TP-03 privileged governance; TP-04 recovery; TP-05 perimeter; TP-13 risk appetite/oversight. | Move highest inherent Critical risks toward High/Moderate residual positions. | IT Manager; Finance Manager; Executive Team | 2026-10-25 | Privileged inventory/review active; tested restore evidence; firewall/VPN baseline complete; quarterly risk governance approved. | Review residual risks R-01, R-03, R-04, R-06 and R-13 for acceptance/treatment continuation.
61–90 Days | Standardize endpoint/platform hygiene and create repeatable operational governance. | TP-06 patch/baseline; TP-15 risk/asset refresh; TP-17 endpoint encryption/compliance; continue legacy reduction. | Reduce ransomware, endpoint and stale-risk exposure; improve operating consistency. | IT Manager; IT Support; IT Security | 2026-11-24 | Patch compliance ≥95%; endpoint encryption ≥98%; quarterly asset review established; threat/vulnerability cadence operating. | Escalate unresolved critical patch/local-admin exceptions.
90+ Days | Build sustainable monitoring, incident readiness, data protection, supplier governance and resilience. | TP-07 legacy migration; TP-08 monitoring; TP-09 IR; TP-10 vendors; TP-11 data controls; TP-12 awareness; TP-14 policy; TP-16 resilience; TP-18 web/domain. | Improve Detect/Respond/Recover and reduce structural supplier/data/legacy gaps. | COO; IT Manager; Procurement; HR; Data Owners | 2026-12-31 | Priority telemetry centralized; IR tabletop complete; vendor program operational; DLP/sharing controls active; core policy suite approved. | Rebaseline CSF Current Profile and enterprise residual risk after evidence validation.

## Workstream Summary
Risk Treatment Workstream Summary
Workstream | Actions | Critical | High | Effort (Days) | Weighted Progress | Latest Due | Lead Owner | Primary Outcome
Identity & Privileged Access | 2 | 2 | 0 | 26 | 15.38% | 2026-10-31 | IT Manager | Strong authentication and controlled privilege
Financial Fraud Prevention | 1 | 1 | 0 | 6 | 50% | 2026-09-30 | Finance Manager | Lower BEC/payment-fraud exposure
Resilience & Ransomware | 2 | 1 | 0 | 28 | 21.43% | 2026-12-31 | IT Manager | Trusted, tested recovery and reduced ransomware impact
Network & Platform Security | 2 | 1 | 1 | 30 | 16.67% | 2026-11-30 | IT Manager | Hardened perimeter/endpoints and reduced exploitability
Legacy Technology Reduction | 1 | 0 | 1 | 30 | 0% | 2026-12-15 | IT Manager | Smaller legacy attack surface and fewer single points of failure
Detection & Response | 2 | 0 | 2 | 38 | 0% | 2026-12-15 | IT Manager | Faster detection, triage, containment and incident decisions
Third-Party Risk | 1 | 0 | 1 | 18 | 0% | 2026-12-15 | COO / Procurement | Governed supplier assurance and privileged external access
Data Protection & Human Factors | 2 | 0 | 2 | 28 | 0% | 2026-12-15 | COO / HR | Reduced data leakage and social-engineering exposure
Governance & Oversight | 3 | 1 | 1 | 30 | 26.67% | 2026-12-15 | COO / IT Manager | Repeatable risk decisions, policies and accountability
Endpoint & Data Security | 1 | 0 | 1 | 10 | 0% | 2026-11-30 | IT Manager | Protected hybrid devices and local data
Public & Domain Security | 1 | 0 | 0 | 8 | 0% | 2026-12-15 | IT Manager / Marketing | Protected website/domain trust and recoverability
Formulas:
Latest Due = MAXIFS('Risk Treatment Plan'!L2:L19,'Risk Treatment Plan'!B2:B19,[Workstream])

## Milestones
Key Remediation Milestones
Milestone | Linked Actions | Owner | Due | Exit Criteria | Evidence | Status | Risk Significance
M-01 Strong Authentication Baseline | TP-01 | IT Manager | 2026-09-15 | All workforce/VPN accounts use MFA; legacy auth disabled. | Authentication coverage report | In Progress | Closes direct initial-access gap for R-03/R-13.
M-02 Finance Fraud Controls | TP-02 | Finance Manager | 2026-09-30 | Independent callback/dual verification fully operating. | Procedure + sample approvals | In Progress | Reduces R-01/R-12 financial fraud likelihood.
M-03 Perimeter Hardening | TP-05 | IT Manager | 2026-10-15 | Supported firmware, MFA, rule review and central logs complete. | Configuration and review evidence | In Progress | Reduces R-13 and ransomware entry paths.
M-04 Trusted Recovery | TP-04 | IT Manager | 2026-10-31 | Immutable backup plus successful timed restore test. | Restore test report | In Progress | Reduces R-06 and ransomware business impact.
M-05 Privileged Access Governance | TP-03 | IT Manager | 2026-10-31 | Privileged accounts recertified; admin separation/hardening in use. | Access review + configuration evidence | Not Started | Reduces R-04 enterprise takeover risk.
M-06 Endpoint Security Standard | TP-06; TP-17 | IT Manager | 2026-11-30 | Patch and encryption targets achieved; local-admin exceptions controlled. | Compliance dashboards | Not Started | Reduces R-05/R-08/R-19.
M-07 Monitoring & Incident Readiness | TP-08; TP-09 | IT Manager | 2026-12-15 | Priority logs centralized; alert model active; IR plan/playbooks/tabletop complete. | Log coverage + tabletop results | Not Started | Reduces R-18 and response impact across top risks.
M-08 Supplier & Data Governance | TP-10; TP-11; TP-14 | COO / IT Manager | 2026-12-15 | Critical vendor process, DLP/sharing controls and policy suite operating. | Vendor pack + DLP review + policies | Not Started | Reduces R-09/R-10/R-11/R-14/R-15/R-19.
M-09 Year-End Resilience Baseline | TP-07; TP-16; TP-18 | COO / IT Manager | 2026-12-31 | Legacy isolation/migration started; failover tested; web/domain recovery documented. | Migration/failover/recovery evidence | Not Started | Reduces R-07/R-16/R-17/R-21/R-22.

## Dependencies
Risk Treatment Dependencies & Constraints
Dependency ID | Dependency / Constraint | Affected Actions | Owner | Impact if Delayed | Mitigation / Workaround | Decision Needed By | Status
D-01 | M365/identity licensing and policy capability | TP-01; TP-03; TP-11 | IT Manager | MFA, conditional access, DLP or privileged controls may be delayed. | Prioritize highest-risk users; use available native controls while licensing is finalized. | 2026-09-05 | Open
D-02 | Backup platform supports immutable/isolated retention | TP-04 | IT Manager | Recovery target cannot be validated at planned strength. | Use separate cloud/offline copy and restricted backup identity as interim control. | 2026-09-15 | Open
D-03 | Business downtime / maintenance windows | TP-05; TP-06; TP-07 | COO / IT Manager | Firmware, patching and legacy isolation may slip. | Pre-approve recurring maintenance windows and communicate service impact. | 2026-09-10 | Open
D-04 | Vendor/MSP cooperation and assurance evidence | TP-10 | Procurement | Supplier-risk treatment cannot be fully evidenced. | Escalate contract requirements; apply least-privilege access until assurance received. | 2026-10-15 | Open
D-05 | Data-owner participation | TP-11 | COO | DLP/export rules may be too broad or ineffective without business context. | Start with customer/HR/finance crown-jewel datasets and named data owners. | 2026-10-15 | Open
D-06 | Executive participation in risk appetite and tabletop | TP-09; TP-13 | COO | Governance and incident decision authority remain informal. | Schedule governance and tabletop dates in advance; provide concise decision packs. | 2026-09-15 | Open
D-07 | Budget for secondary connectivity / infrastructure changes | TP-16; TP-07 | COO | Resilience improvements may extend beyond year-end. | Document accepted interim risk; prioritize procedural recovery and diverse mobile failover. | 2026-11-01 | Open

## Success Metrics
Risk Treatment Success Metrics
Metric ID | Metric | Baseline | Target | Owner | Frequency | Evidence Source | Linked Actions
KRI-01 | Workforce/VPN MFA coverage | Incomplete / exceptions exist | 100% | IT Manager | Monthly | Identity/VPN configuration export | TP-01
KRI-02 | Privileged accounts recertified | Ad hoc | 100% quarterly | IT Manager | Quarterly | Privileged access review | TP-03
KRI-03 | Critical/high patch compliance within SLA | Mixed cadence | ≥95% | IT Support Lead | Monthly | Patch compliance dashboard | TP-06
KRI-04 | Managed laptop encryption coverage | Requires validation | ≥98% | IT Support Lead | Monthly | Endpoint compliance dashboard | TP-17
KRI-05 | Quarterly backup restore success | Ad hoc testing | 100% planned tests succeed | Systems Administrator | Quarterly | Restore test report | TP-04
KRI-06 | Priority security log-source coverage | Fragmented | ≥90% of defined priority sources | IT Security Analyst | Monthly | Logging coverage matrix | TP-08
KRI-07 | Critical alert ownership within SLA | Informal | ≥95% | IT Security Analyst | Monthly | Incident/SIEM ticket report | TP-08; TP-09
KRI-08 | Critical vendor annual assurance coverage | Inconsistent | 100% | Procurement | Annual | Vendor assurance register | TP-10
KRI-09 | Anonymous external sharing enabled | Requires review | Disabled by default | IT Security Analyst | Quarterly | M365 sharing report | TP-11
KRI-10 | Security awareness completion | Not formally measured | ≥95% annually | HR Manager | Quarterly | Training report | TP-12
KRI-11 | Phishing simulation repeat-click trend | No baseline | Downward trend / targeted remediation | HR / IT Security | Quarterly | Phishing simulation report | TP-12
KRI-12 | Open Critical/High treatment actions overdue | 0 baseline defined | 0 overdue without approved exception | COO / IT Manager | Monthly | Treatment-plan dashboard | All

## Methodology
Risk Treatment Planning Methodology
Treatment Prioritization
Actions were prioritized using the Project 2 enterprise risk register, residual risk, NIST CSF 2.0 control gaps, asset criticality and attack-path dependencies. Critical actions address direct initial-access, financial fraud, privileged takeover, perimeter exposure, recovery or governance weaknesses. High actions address material but less immediate structural weaknesses. Medium actions primarily improve sustainability, resilience or lower-tier risks.
Effort and Budget Assumptions
Estimated effort is expressed in person-days for planning purposes and is intentionally approximate. Budget Tier is qualitative: Low = primarily staff/configuration effort; Medium = likely licensing, consulting or implementation cost; High = material infrastructure, migration or service-provider cost; Very High = major transformation. No currency estimate is provided because this is a simulated portfolio environment and vendor pricing would vary.
Completion & Schedule Logic
Completion % is formula-driven from Status: Implemented/Accepted = 100%, In Progress = 50%, Not Started/Blocked = 0%. This is a simple portfolio tracking convention rather than a measurement of technical control effectiveness. The Executive Dashboard calculates effort-weighted progress using person-days so a large unfinished workstream is not masked by several small completed actions. Schedule flags are calculated relative to the assessment date of 26 August 2026.
Residual Risk Validation
A treatment action should not automatically reduce a residual risk rating merely because it is marked complete. Residual risk should be re-assessed only after the success criteria and required evidence demonstrate that the control is operating as intended. For example, backup risk is not reduced by purchasing an immutable-backup feature; it is reduced after configuration is verified and a timed restoration test succeeds.

## References
Source | Use in Treatment Plan | URL | Notes
NIST Cybersecurity Framework 2.0 | Primary outcome framework supporting remediation priorities across Govern, Identify, Protect, Detect, Respond and Recover. | https://www.nist.gov/cyberframework | Used as a risk-informed control framework; no certification claim.
NIST SP 800-30 Rev. 1 — Guide for Conducting Risk Assessments | Supports likelihood, impact, threat, vulnerability and risk-treatment context. | https://csrc.nist.gov/pubs/sp/800/30/r1/final | Supporting methodology.
NIST CSF 2.0 Quick Start Guides | Supports organizational profiles, enterprise risk management, supply-chain risk and implementation planning. | https://www.nist.gov/cyberframework/quick-start-guides | Used as implementation reference.
NIST SP 1308 — CSF 2.0: Cybersecurity, Enterprise Risk Management, and Workforce Management QSG | Supports communicating and integrating cyber risk across enterprise decisions and workforce responsibilities. | https://www.nist.gov/publications/nist-cybersecurity-framework-20-cybersecurity-enterprise-risk-management-and-workforce | Published March 2026.
ISO/IEC 27001:2022 | Supporting information-security management/control crosswalk used elsewhere in Project 2. | https://www.iso.org/standard/27001 | Reference only; no certification claim.
Portfolio Disclaimer
This workbook is a simulated cybersecurity risk-treatment plan for IslandLink Business Services Ltd., a fictional Jamaican company. Risks, owners, dates, effort estimates, budget tiers, controls, success criteria and residual-risk objectives are illustrative portfolio assumptions. The plan is not legal advice, a regulatory determination, a NIST certification or evidence of implementation by a real organization.

## Lists
Priority | Status | Treatment | Budget Tier | Phase | Evidence Status
Critical | Not Started | Mitigate | Low | 0–30 Days | Missing
High | In Progress | Transfer | Medium | 31–60 Days | Planned
Medium | Implemented | Avoid | High | 61–90 Days | Partial
Low | Blocked | Accept | Very High | 90+ Days | Available
Accepted